## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-SWEN-261-04-D-SICA
Testing Team Name | fill in when doing cross-team testing
PLEASE NOTE THAT ANY USER STORY THAT IF A USER STORY IS NOT TICKED IN SPRINT 2 OR SPRINT 3, THEN IT HAS NOT BEEN IMPLMENTED YET AND SHOULD NOT BE TESTED.

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
AS a User I WANT to submit a request to get the products in the inventory whose name contains the given text SO THAT I have access to only those products. | **Given** I am a customer **when** I search through products **then** I expect the matching products to be listed instantly. | Pass | SJ; 03/21/23
| **Given** I am a customer, **when** I search for a product, **then** products with a different case should be matched. | Pass | SJ; 03/21/23
| **Given** I am a customer, **when** I search for a non-existent, **then** nothing is shown. | Pass | SJ; 03/21/23
| **Given** that I am on the products page **when** there are products in the inventory **then** I see each product and short description. | Pass | SJ; 03/21/23
AS a user, I WANT a shopping cart SO THAT I can keep track of items I want to buy. | **Given** that I want to buy a product **when** I press add to shopping cart **then** I can see all products added to shopping cart in one location. | Pass | SJ; 03/21/23
| **Given** that I no longer want to buy something **when** I press remove from shopping cart **then** the item is removed from shopping cart. | Pass | SJ; 03/21/23
| **Given** I want to buy multiple/less of one product **when** I increase/decrease the amount of the item **then** the number of product in shopping cart is decreased. | Pass | SJ; 03/21/23
AS a customer I WANT to have a login SO THAT I can save my products. | **Given** I am a customer without an account, **when** I go to login, **then** the Estore creates an account for me. | Pass | IK; 03/08/23
| **Given** I am a customer with an account, **when** I go to login, **then** the EStore returns the account I already created. | Pass | IK; 03/08/23
| **Given** I am a customer with an account, **when** I create my account, **then** I have a shopping cart automatically created for me. | Pass | IK; 03/08/23
AS a owner, I WANT a product inventory SO THAT I can add, remove, and edit the product data in the inventory. | **Given** an admin **when** I navigate to the homepage **then** I expect all of the current products and quantity to be displayed and listed. | Pass | CL; 03/13/23
| **Given** I am an admin **when** I click the delete button, **then** the product is fully removed from the inventory. | Pass | CL; 03/13/23
| **Given** I am an admin, **when** I click the add button, **then** the product is added to the inventory and the list is updated. | Pass | CL; 03/13/23
| **Given** I am an admin, **when** I edit the product, **then** the product is edited, saved, and the list is updated. | Pass | CL; 03/13/23
AS a owner I WANT to add a admin login SO THAT I have access to manipulate products. | **Given** I am an admin **when** give admin credential **then** I expect to have admin tools at my disposal. | Pass | AK; 03/15/23
| **Given** I am an admin, **when** I go to the homepage, **then** the cart should not be visible for me. | Pass | AK; 03/15/23
| **Given** I am an admin, **when** I click a product, **then** I cannot see the product detail page. | Pass | AK; 03/15/23
As a customer I want to be able to see the description so that I can know if the keyboard is something I would like to invest in. | **Given** I am an admin **when** create a product **then** I should be able to add a description at the time of creation. |  |  | Pass | SJ; 04/04/23
| **Given** I am a customer **when** I request a product **then** I should be able to see the product description. |  |  | Pass | SJ; 04/04/23
As a customer, I want the ability to checkout, so that I can purchase my products. | **Given** I am a customer **when** I click the checkout button **then** I am navigated to a page that allows me to enter checkout details.
**Given** I am a customer **when** I click the purchase button **then** I am navigated to an order confirmation page.
**Given** I am a customer **when** I am on the checkout page **then** I can go abandon the checkout process whenever I want.
As a customer I want to pick out my keyboard size so that I can build my desired keyboard. | **Given** I am a customer who wants a specific keyboard size **when** I enter the keyboard page **then** I expect to see all the different keyboard sizes and be able to sort keyboards based on size.
As a customer I want to pick out my switches so that I can build my desired keyboard. | **Given** I am a customer who wants a specific switch **when** I enter the switch page **then** I expect to see all the different switches and be able to add them to my shopping cart.
As a customer I want to pick out my keycaps so that I can build my desired keyboard. | **Given** I am a customer who wants a specific keycap **when** I enter the keycap page **then** I expect to see all the keycaps I can choose from and be able to add them to my shopping cart.
As a customer I want to pick out my keyboard case so that I can build my desired keyboard. | **Given** I am a customer who wants a specific keyboard case **when** I click on the case options **then** I expect to see all the different keyboard cases and the ability to add them to cart.
As a developer, I want to be able to customize my keyboard so that I can design it to my preferences. | **Given** that I am a customer who wants a keyboard **when** I choose the option for a custom keyboard **then** I expect to be able to customize a keyboard.